## Deliverables
DELIVERABLE TRACKER
Project: |  | Doc no: PM-EXE-006 | Rev: 01 | Date: | Prepared by:
Yellow cells = fill in. Grey italic row = example — overwrite it. Formulas calculate automatically.
ID | Deliverable | Type | Responsible | Planned date | Submitted date | Rev | Status | Approved date | Days late | Remarks
DLV-001 | Tower A curtain wall shop drawings — L1–L10 | Drawing | Design | 2026-07-10 | 2026-07-14 | B | Code B |  | 4 | Resubmit with comments
| OVERDUE OPEN DELIVERABLES | [7 empty] | 1
Formulas:
Days late = IF(NOT(ISNUMBER([Date:])),"",IF(NOT(ISNUMBER([Prepared by:])),IF(TODAY()>[Date:],TODAY()-[Date:],0),IF([Prepared by:]>[Date:],[Prepared by:]-[Date:],0)))