Extension of time (EOT) claim

[Project name] — [Contractor] — Claim ref [EOT-01]

| Field | Detail |
| --- | --- |
| Contract | [Contract title / no] |
| Notice reference | [NOT-001 dated DD/MM/YYYY] |
| Current completion date | [DD/MM/YYYY] |
| EOT claimed | [xx] calendar days |
| Revised completion sought | [DD/MM/YYYY] |

# 1. Executive summary

[One paragraph: the event, the entitlement clause, the delay caused to the critical path, days claimed, and costs if applicable.]

# 2. Contractual basis

[Cite entitlement clauses: e.g. Sub-Clause 8.4 (Extension of Time for Completion), 20.1 (Notices); list the qualifying cause — variation, late information, employer delay, exceptional weather, etc.]

# 3. Event narrative and records

| Date | Event | Record ref |
| --- | --- | --- |
| [DD/MM] | [What happened] | [Letter / MOM / diary ref] |
| [DD/MM] | [Development] | [Ref] |
| [DD/MM] | [Event ceased / continuing] | [Ref] |

# 4. Cause and effect

[Link the event to specific programme activities: which activities could not proceed, why no workaround was reasonably available, and how the delay propagated to the critical path.]

# 5. Delay analysis

Method: [Time impact analysis / impacted as-planned / as-planned vs as-built], using programme revision [P-rev].

| Activity | Planned dates | Actual / forecast | Delay (days) |
| --- | --- | --- | --- |
| [Activity ID — description] | [start–finish] | [start–finish] | [xx] |
| [Activity ID — description] | [start–finish] | [start–finish] | [xx] |
| Net critical delay |  |  | [xx] |

# 6. Prolongation costs (if claimed)

| Cost head | Basis | Amount |
| --- | --- | --- |
| Site staff & supervision | [rate × period] | [ ] |
| Site facilities & overheads | [rate × period] | [ ] |
| Equipment standing | [rate × period] | [ ] |
| Head office overheads | [formula / basis] | [ ] |
| Total |  | [ ] |

# 7. Attachments

[Programme extracts, notice correspondence, site records, photographs, instructed variations, weather records.]