## Portfolio
EXECUTIVE DASHBOARD — PORTFOLIO
Project: |  | Doc no: PM-RPT-004 | Rev: 01 | Date: | Prepared by:
Yellow cells = fill in. Grey italic row = example — overwrite it. Formulas calculate automatically.
Project | Contract value (SAR) | Plan % | Actual % | Variance | SPI | CPI | Value done (SAR) | Open risks | RAG | Remarks
Coastal Tower — Facade | 2450000 | 68% | 62% | -6% | 0.96 | 1.02 | 771000 | 4 | GREEN
PORTFOLIO | 2450000 |  | 62% |  |  |  | 771000 | 4
Weighted progress = value-weighted (SUMPRODUCT). RAG from SPI/CPI thresholds — editable.