## Index
Interface Matrix
[PROJECT NAME] — Twin Towers Façade Package ¦ Façade Contractor ↔ Main Contractor & others
Type key:
P = Physical interface ¦ I = Information / approval ¦ A = Access / logistics ¦ S = Schedule / sequence
Sheet | Purpose
Interface Matrix | Tracked interfaces between us, the Main Contractor and other trades
Scope Responsibility Split | What is by Façade Contractor / Main Contractor / Others, per element

## Interface Matrix
Interface Matrix — Façade Package
Each interface = a handover of information, physical work, access or sequence. Track to closure. Blue = input.
ID | Interface description | Façade system / location | Provided by | Received by | Type | Information / deliverable required | Required by | Status | Remarks
IF-01 | Setting-out datum, gridlines & benchmarks | All / both towers | Main Contractor | Façade | I | Survey control & datum issued and verified | [date] | Open
IF-02 | Slab-edge level & verticality survey | Per zone / floor | Main Contractor | Façade | I | As-built slab survey vs tolerance before bracket fixing | [date] | Open
IF-03 | Cast-in embeds / anchor channels | Slab edges | [confirm] | Façade | P | Embeds installed to approved positions (or by us — confirm) | [date] | Open
IF-04 | Slab-edge concrete / upstand / kerb | Perimeter | Main Contractor | Façade | P | Edge complete, square, weather-line ready | [date] | Open
IF-05 | Structure handover (zone) weather-tight | Per install zone | Main Contractor | Façade | S | Structure complete & released for façade install | [date] | Open
IF-06 | Perimeter fire-stopping / smoke seal | Slab-to-façade gap | [confirm split] | Both | P | Detail & responsibility agreed; install sequence | [date] | Open
IF-07 | Waterproofing / DPM interface (base & parapet) | Base, roof, parapet | Main Contractor | Façade | P | Membrane lapped/terminated to façade detail | [date] | Open
IF-08 | Hoisting / crane time allocation | Both towers | Main Contractor | Façade | A | Lifting windows & crane schedule for façade loads | [date] | Open
IF-09 | Material hoist / common access | Both towers | Main Contractor | Façade | A | Hoist availability & timings | [date] | Open
IF-10 | Power supply for BMU / mast climbers | Roof / façade | Main Contractor | Façade | A | Temporary power points & capacity | [date] | Open
IF-11 | Laydown / storage areas | Site / floors | Main Contractor | Façade | A | Allocated laydown & just-in-time storage zones | [date] | Open
IF-12 | BMU rails / soffit fixings at roof crown | Roof | [Steelwork/MC] | Façade | P | Support/fixing provision & tolerances | [date] | Open
IF-13 | MEP penetrations / functional louver intake | Louvers / façade | MEP contractor | Façade | P | Coordinated openings, duct interface, fire dampers | [date] | Open
IF-14 | Internal finishes interface (reveals/sills) | Openings, doors | Fit-out contractor | Façade | P | Reveal/sill detail & sequence at doors & windows | [date] | Open
IF-15 | Balustrade to floor finish / waterproofing | Balconies/terraces | Both | Façade | P | Fixing & waterproofing interface at balustrade base | [date] | Open
IF-16 | Lightning protection bonding | Façade / roof | MEP / MC | Façade | P | Bonding points & continuity to façade/louvers | [date] | Open
IF-17 | Builder's work openings / penetrations | Various | Main Contractor | Façade | P | BWIC schedule & dimensions | [date] | Open
IF-18 | Movement joints alignment with structure | All | Main Contractor | Façade | I | Structural movement data for joint design | [date] | Open
IF-19 | Protection of installed façade (following trades) | All | Main Contractor | Both | S | Protection regime & damage/back-charge process | [date] | Open
IF-20 | Snagging & access for handover | Per zone | Both | Both | S | Access for joint inspection & punch close-out | [date] | Open

## Scope Responsibility Split
Scope Responsibility Split
Confirm each line against the subcontract. ✓ = responsible party. Adjust as agreed.
Element / work item | By Façade Contractor | By Main Contractor | By Others | Notes / confirm
Façade design / shop drawings / calculations | ✓ |  |  | Design responsibility per contract
Stick curtain wall supply & install | ✓
Lift-and-slide doors supply & install | ✓
Glass balustrade supply & install | ✓
Aluminium cladding supply & install | ✓
Roof crown louvers supply & install | ✓
Brackets / anchors design & supply | ✓ |  |  | Confirm cast-in vs post-fix
Cast-in embeds / anchor channels |  | ✓ |  | Confirm — may be by us
Primary & secondary structure |  | ✓
Slab edge concrete / upstands |  | ✓
Perimeter fire-stopping / smoke seal |  |  | ✓ | Confirm split
Waterproofing / DPM (base, roof, parapet) |  | ✓
Temporary power / water |  | ✓
Common tower crane / hoist |  | ✓
Façade-specific access (mast climbers/BMU) | ✓ |  |  | Confirm BMU permanent vs temp
Scaffolding / common access |  | ✓
Internal finishes / fit-out |  |  | ✓
MEP services & louver functional connection |  |  | ✓
Builder's work in connection (BWIC) |  | ✓
Protection of installed façade |  | ✓ |  | Following-trade damage back-charged
Cleaning at handover | ✓ |  |  | Confirm final clean scope