## Manpower
Manpower plan — [Project name]
Trade / role | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Site manager | bar: W1 to W12
Foreman | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Steel fixers | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Glaziers / installers | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Welders | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Helpers / labourers | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
QA/QC inspector | bar: W1 to W12
HSE officer | bar: W1 to W12
Total (planned)
Tip: select the Total (planned) row and insert a column chart for the manpower histogram.