## Mob-Demob
Mobilization & demobilization plan — [Project name]
Ref | Phase | Task | Responsible | Planned date | Actual date | Status | Remarks
M-01 | Mobilization | Contract signed & advance payment secured | [PM / QS] |  |  | Not started
M-02 | Mobilization | Insurances & bonds in place (CAR, workmen, advance) | [Commercial] |  |  | Not started
M-03 | Mobilization | Permits, NOCs & authority approvals to start | [PM] |  |  | Not started
M-04 | Mobilization | Site offices, welfare & storage established | [Site manager] |  |  | Not started
M-05 | Mobilization | Power, water & IT/comms connected | [Site manager] |  |  | Not started
M-06 | Mobilization | Laydown & fabrication areas agreed and marked | [Site manager] |  |  | Not started
M-07 | Mobilization | Hoarding, signage & security in place | [HSE] |  |  | Not started
M-08 | Mobilization | Key staff mobilized (visas, inductions, IDs, gate passes) | [HR / Admin] |  |  | Not started
M-09 | Mobilization | Plant & equipment delivered and inspected | [Plant] |  |  | Not started
M-10 | Mobilization | HSE plan approved; first toolbox talk held | [HSE] |  |  | Not started
M-11 | Mobilization | Baseline programme & method statements submitted | [Planner] |  |  | Not started
D-01 | Demobilization | Plant & equipment off-hired and removed | [Plant] |  |  | Not started
D-02 | Demobilization | Temporary works & site facilities removed | [Site manager] |  |  | Not started
D-03 | Demobilization | Site reinstated & waste cleared | [Site manager] |  |  | Not started
D-04 | Demobilization | Surplus materials returned / transferred | [Procurement] |  |  | Not started
D-05 | Demobilization | Staff demobilized / reassigned; accounts closed | [HR / Admin] |  |  | Not started
D-06 | Demobilization | Utilities disconnected & permits closed out | [PM] |  |  | Not started
D-07 | Demobilization | Handover walkthrough done; keys & passes returned | [PM] |  |  | Not started