## Procurement
Procurement & delivery tracker — [Project name]
Ref | Material / package | Spec ref | Supplier | PO no | PO date | Lead time (wks) | Required on site | ETA | Status | Critical (Y/N) | Delivered date | Remarks
PRC-001 | [Aluminium profiles — system] | [Spec §] | [Supplier] | [PO-001] |  | 12 |  |  | PO placed | Y |  | [Long-lead]
PRC-002 | [Glass — DGU panels] | [Spec §] | [Supplier] |  |  | 10 |  |  | Enquiry | Y
PRC-003 | [Fixing brackets & anchors] | [Spec §] | [Supplier] |  |  | 4 |  |  | Quotation received | N
PRC-004 | [Sealant & gaskets] | [Spec §] | [Supplier] |  |  | 3 |  |  | Fabrication | N
Status flow: Enquiry → Quotation received → PO placed → Fabrication → Shipping → Customs → Delivered. Track long-lead items weekly.