## Product backlog
Product backlog — [Product / project]
ID | Epic / theme | User story (As a… I want… so that…) | Priority (MoSCoW) | Points | Value | Status | Target sprint | Acceptance criteria (summary)
PBL-001 | [Accounts] | As a user, I want to reset my password, so that I can regain access | Must | 3 | High | Ready | S1 | Given a valid email, when I request a reset, then a link is sent
PBL-002 | [Accounts] | As a user, I want to sign in with my email, so that I can reach my workspace | Must | 5 | High | Ready | S1 | [Given / when / then]
PBL-003 | [Reporting] | As a manager, I want a weekly summary, so that I can brief my team | Should | 8 | Medium | Refinement | S2 | [Given / when / then]
PBL-004 | [Onboarding] | As a new user, I want a guided setup, so that I can start quickly | Could | 5 | Medium | New |  | [Given / when / then]
PBL-005 | [Admin] | As an admin, I want to export data, so that I can archive it | Won’t (now) | 3 | Low | New |  | [Given / when / then]
MoSCoW: Must · Should · Could · Won’t (this release). Points on the Fibonacci scale (1, 2, 3, 5, 8, 13). Keep the top of the backlog refined and estimated.