## Project Info
Project Control Workbook
Master register set — Progress · Cost · Risk · Scope · Responsibility
| PROJECT IDENTITY |  | SCHEDULE & STATUS
| Project Name | New Facility Fit-Out (sample) | Planned Start | 2026-02-01
| Project Code | PRJ-2026-014 | Planned Finish | 2026-09-30
| Project Manager | A. Project Manager | Data / Report Date | 2026-06-26
| Sponsor | Operations Director | Baseline Budget | 920000
| Client / Department | Internal — Facilities | Overall Status | On Track
| Currency | SAR | Version / Rev | Rev 0 — Baseline
How to use: Cells tinted cream are inputs — type over them. Black/green cells are formulas that update automatically. Each register links into the Dashboard. Set your currency above; amount columns are unformatted numbers so they suit any currency. Add rows inside the shaded tables (insert above the last row to keep formulas intact). Tabs flow left→right: Info · Dashboard · Scope · WBS · RBS · RACI · Progress · Budget · Variations · Risks · Issues.

## Dashboard
Project Dashboard
Live roll-up of progress, cost, risk, issues and change — auto-updates from every register
| Project | Manager | Status | Report Date
| New Facility Fit-Out (sample) | A. Project Manager | On Track | 2026-06-26
| OVERALL PROGRESS |  | COST VARIANCE |  | % BUDGET SPENT
| 52.5% |  | 46000 |  | 39.45%
| OPEN RISKS |  | HIGH RISKS |  | OPEN ISSUES
| 5 |  | 1 |  | 2
| COST SUMMARY |  |  |  | RISK BY RATING
| Baseline Budget |  | 920000 |  | High | 1
| Approved Variations |  | 18000 |  | Medium | 3
| Revised Budget |  | 938000 |  | Low | 1
| Committed |  | 440000 |  | Approved Var. Cost | 18000
| Actual to Date |  | 370000 |  | Tasks In Progress | 3
| Estimate at Completion |  | 892000 |  | Tasks Complete | 2

## Scope Statement
Project Scope Statement
Define what the project will and will not deliver — the baseline for change control
| 1. Project Purpose / Justification | Why this project exists — the business need or opportunity it addresses.
[ type here ]
| 2. Project Objectives | Measurable objectives (SMART). e.g. Deliver X by [date] within [budget] meeting [standard].
[ type here ]
| 3. Project Description | A concise narrative of the work, approach, and the solution being delivered.
[ type here ]
| 4. Key Deliverables | Major tangible outputs the project will produce and hand over (link to WBS).
[ type here ]
| 5. Acceptance Criteria | Conditions that must be met for deliverables to be accepted by the sponsor/client.
[ type here ]
| 6. In Scope | Work, features, locations, and functions explicitly included.
[ type here ]
| 7. Out of Scope / Exclusions | Work explicitly NOT included — prevents scope creep. Be specific.
[ type here ]
| 8. Key Milestones | Major schedule checkpoints with target dates.
[ type here ]
| 9. Assumptions | Factors taken to be true for planning. If wrong, they become risks.
[ type here ]
| 10. Constraints | Fixed limits — budget cap, deadline, resources, regulations, technology.
[ type here ]
| 11. Key Stakeholders | Sponsor, client, end-users, approvers, and other affected parties.
[ type here ]
| 12. Approval | Sign-off names, roles, dates confirming the scope baseline.
[ type here ]

## WBS
Work Breakdown Structure (WBS)
Decompose the scope into deliverables and work packages — the backbone for cost, schedule and RACI
| WBS ID | Level | Element / Work Package | Description | Deliverable / Output | Owner
| 1 | 1 | Project Management | Planning, control, reporting, governance | PM plan, reports | PM
| 1.1 | 2 | Project Planning | Schedule, budget, registers set-up | Baseline plan | PM
| 1.2 | 2 | Monitoring & Control | Progress, cost, risk tracking | Status reports | PM
| 2 | 1 | Design | Concept through detailed design | Approved design pack | Design Lead
| 2.1 | 2 | Concept Design | Options and selection | Concept report | Designer
| 2.2 | 2 | Detailed Design | Drawings & specifications | IFC drawings | Designer
| 3 | 1 | Procurement | Sourcing materials & subcontracts | Signed contracts | Procurement
| 3.1 | 2 | Long-lead Items | Order critical equipment | POs issued | Procurement
| 4 | 1 | Execution / Build | Physical delivery of works | Completed works | Site Manager
| 4.1 | 2 | Enabling Works | Site prep & services | Site ready | Site Manager
| 4.2 | 2 | Main Works | Core construction / install | Installed works | Site Manager
| 5 | 1 | Testing & Commissioning | Verify performance | T&C certificates | QA Lead
| 6 | 1 | Handover & Closeout | Final acceptance & close | Closeout report | PM

## RBS
Risk Breakdown Structure (RBS)
Hierarchy of risk sources / categories — the taxonomy used to classify entries in the Risk Register
| RBS ID | Level | Category | Sub-Category | Typical Sources / Examples
| 1 | 1 | Technical |  | Design, technology, quality, performance
| 1.1 | 2 | Technical | Design & Requirements | Incomplete scope, changing requirements
| 1.2 | 2 | Technical | Quality & Performance | Defects, not meeting acceptance criteria
| 2 | 1 | External |  | Outside the project's control
| 2.1 | 2 | External | Regulatory / Legal | Permits, compliance, law changes
| 2.2 | 2 | External | Market / Supplier | Price volatility, supplier failure, lead times
| 2.3 | 2 | External | Weather / Site | Conditions, access, ground conditions
| 3 | 1 | Organizational |  | Internal company factors
| 3.1 | 2 | Organizational | Resources | Availability, skills, competing priorities
| 3.2 | 2 | Organizational | Funding | Budget approval, cash flow
| 4 | 1 | Project Management |  | Planning & control processes
| 4.1 | 2 | Project Management | Estimating | Cost / duration under-estimation
| 4.2 | 2 | Project Management | Communication | Stakeholder alignment, reporting gaps
| 5 | 1 | Commercial |  | Contract & financial exposure
| 5.1 | 2 | Commercial | Contractual | Liabilities, penalties, claims

## RACI
Responsibility Assignment Matrix (RACI)
R = Responsible · A = Accountable · C = Consulted · I = Informed (one A per row)
| Activity / Deliverable | Sponsor | Project Manager | Design Lead | Procure- ment | Site Manager | QA Lead | Client | Finance
| Project plan & baselines | I | A | C | C | C | C | I | C
| Scope statement sign-off | A | R | C | I | I | I | C | I
| Concept design | I | A | R | I | C | C | C | I
| Detailed design & drawings | I | A | R | C | C | C | I | I
| Procurement & contracts | I | A | C | R | C | I | I | C
| Site execution / build | I | A | I | C | R | C | I | I
| Quality inspections | I | A | C | I | C | R | I | I
| Testing & commissioning | I | A | C | I | C | R | C | I
| Risk & issue management | C | A | C | C | C | C | I | C
| Change / variation approval | A | R | C | C | C | I | C | C
| Progress & cost reporting | I | A | I | I | I | I | I | C
| Handover & closeout | A | R | C | C | C | C | C | I

## Progress
Progress Tracker
Task-level status; weighted % roll-up feeds the Dashboard
| WBS ID | Task / Deliverable | Owner | Plan Start | Plan Finish | Actual / Fcast Finish | Weight | % Complete | Status | Sched Var (d) | Notes
| 1.1 | Project planning | PM | 2026-02-01 | 2026-02-21 | 2026-02-20 | 10 | 100% | Complete | -1
| 2.1 | Concept design | Designer | 2026-02-22 | 2026-03-21 | 2026-03-25 | 15 | 100% | Complete | 4
| 2.2 | Detailed design | Designer | 2026-03-22 | 2026-05-02 | 2026-05-10 | 20 | 85% | In Progress | 8
| 3.1 | Long-lead procurement | Procurement | 2026-04-01 | 2026-05-15 | 2026-05-20 | 10 | 60% | In Progress | 5
| 4.1 | Enabling works | Site Manager | 2026-05-10 | 2026-06-10 |  | 15 | 30% | In Progress
| 4.2 | Main works | Site Manager | 2026-06-11 | 2026-08-20 |  | 20 | 0% | Not Started
| 5 | Testing & commissioning | QA Lead | 2026-08-21 | 2026-09-15 |  | 7 | 0% | Not Started
| 6 | Handover & closeout | PM | 2026-09-16 | 2026-09-30 |  | 3 | 0% | Not Started
| WEIGHTED PROGRESS | [6 empty] | 52.5%

## Budget
Budget & Cost Control
Baseline → revised → actual → forecast. Approved variations flow in automatically from the Variations log.
| WBS ID | Cost Item | Category | Baseline Budget | Approved Variations | Revised Budget | Committed | Actual to Date | Forecast to Complete | EAC | Variance | % Spent | Notes
| 1 | Project management | Indirect | 60000 | 0 | 60000 | 30000 | 32000 | 15000 | 47000 | 13000 | 53.33%
| 2 | Design fees | Design | 120000 | 0 | 120000 | 120000 | 118000 | 2000 | 120000 | 0 | 98.33%
| 3 | Materials & equipment | Direct | 380000 | 18000 | 398000 | 200000 | 150000 | 230000 | 380000 | 18000 | 37.69%
| 4 | Construction labour | Direct | 260000 | 0 | 260000 | 90000 | 70000 | 190000 | 260000 | 0 | 26.92%
| 5 | Testing & commissioning | Direct | 45000 | 0 | 45000 | 0 | 0 | 45000 | 45000 | 0 | 0%
| 6 | Contingency | Reserve | 55000 | 0 | 55000 | 0 | 0 | 40000 | 40000 | 15000 | 0%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| TOTAL |  |  | 920000 | 18000 | 938000 | 440000 | 370000 | 522000 | 892000 | 46000 | 39.45%

## Variations
Variations / Change Log
Track change requests and their cost & schedule impact. Approved items flow into the Budget automatically (matched by WBS ID).
| Var ID | Description | WBS ID | Type | Date Raised | Cost Impact | Sched Impact (d) | Status | Raised By | Approved By | Notes
| CR-001 | Add second electrical riser | 3 | Scope | 2026-04-12 | 18000 | 5 | Approved | Site Manager | Sponsor
| CR-002 | Upgrade flooring spec | 4 | Quality | 2026-05-02 | 9500 | 0 | Under Review | Client | -
| CR-003 | Accelerate T&C schedule | 5 | Time | 2026-05-20 | 4000 | -3 | Submitted | PM | -
| TOTAL APPROVED COST IMPACT |  |  |  |  | 18000

## Risk Register
Risk Register
Score = Probability × Impact (1–5 each). Rating drives the heat colour. Categories come from the RBS.
| Risk ID | Category | Risk Description | Cause | Effect | P | I | Score | Rating | Response | Mitigation Actions | Owner | Target Date | Status
| R-01 | External | Long-lead equipment delayed | Supplier capacity | Schedule slip | 4 | 4 | 16 | High | Mitigate | Order early; dual-source | Procurement | 2026-05-01 | Open
| R-02 | Technical | Design changes after IFC | Late client input | Rework & cost | 3 | 4 | 12 | Medium | Mitigate | Freeze scope; change control | Design Lead | 2026-04-15 | In Progress
| R-03 | Organizational | Key resource unavailable | Competing projects | Slower delivery | 3 | 3 | 9 | Medium | Mitigate | Backfill plan; cross-train | PM | 2026-06-01 | Open
| R-04 | Commercial | Cost overrun on materials | Price volatility | Budget breach | 3 | 4 | 12 | Medium | Transfer | Fixed-price PO; contingency | Procurement | 2026-05-10 | Open
| R-05 | External | Adverse weather on site | Seasonal | Lost days | 2 | 3 | 6 | Low | Accept | Float in schedule | Site Manager | 2026-07-01 | Open

## Issue Register
Issue Register
Active problems needing resolution (a risk that has occurred becomes an issue).
| Issue ID | Issue Description | Raised By | Date Raised | Priority | Impact | Action / Resolution | Owner | Target Date | Status | Date Closed
| I-01 | Drawing clash at riser | Site Manager | 2026-05-08 | High | Rework on site | Coordinate; reissue detail | Design Lead | 2026-05-15 | In Progress
| I-02 | Material delivery short | Procurement | 2026-05-18 | Medium | Partial install delay | Expedite balance | Procurement | 2026-05-25 | Open