## Index
Registers & Forms
[PROJECT NAME] — Twin Towers Façade Package ¦ Companion to 05_Project_Control_Pack.xlsx
Blue text = input ¦ Black text = formula
Sheet | Purpose
Risk Register | Identify, score (P×I) and track risks & mitigations
RFI Log | Requests for information — open/closed and ageing
Submittal Register | Drawings / calcs / samples — submitted, reviewed, status
NCR Log | Non-conformance reports — disposition and close-out
Variation Register | Changes / variations — time & cost impact
Payment Application | Monthly interim payment application (IPA)
Daily Site Report | Daily record — manpower, plant, activities, deliveries, HSE
2-Week Look-Ahead | Short-term rolling installation plan
ITP | Inspection & Test Plan with hold/witness points
Snagging List | Punch list — defects and close-out

## Risk Register
Risk Register
Score = Probability × Impact (1–5 each). Rating: High ≥15, Medium 8–14, Low ≤7.
ID | Date raised | Category | Risk description | Cause | Impact if it occurs | P (1-5) | I (1-5) | Score | Rating | Response | Mitigation actions | Owner | Due date | Status
R-01 | [date] | Engineering | Slow drawing approvals | Long consultant review | Delays fabrication & install | 4 | 5 | 20 | High | Reduce | Lock approval SLA; submit early; escalation path | Eng Mgr | [date] | Open
R-02 | [date] | Quality | Performance mock-up fails testing | Design / workmanship | Re-design, re-test, bulk-order slip | 3 | 5 | 15 | High | Reduce | Early VMU/PMU; conservative design; spare test slot | Eng Mgr | [date] | Open
R-03 | [date] | Procurement | Long-lead / price escalation | Commodity market | Cost & schedule | 3 | 4 | 12 | Medium | Transfer | Early POs; price-lock; escalation clause; alt vendors | Proc Mgr | [date] | Open
R-04 | [date] | Interface | Slab-edge tolerance clashes | Structure out of tolerance | RFIs, rework at install | 4 | 3 | 12 | Medium | Reduce | Early survey & tolerance protocol; adjustable brackets | PM | [date] | Open
R-05 | [date] | Resource | Concurrent two-tower resource conflict | Both towers active | Productivity loss | 3 | 3 | 9 | Medium | Reduce | Resource-level both towers; capacity plan | Site Mgr | [date] | Open
R-06 | [date] | HSE | Work-at-height incident | Working at height / glass | Harm, stoppage, liability | 2 | 5 | 10 | Medium | Reduce | RAMS, training, exclusion zones, audits | HSE Mgr | [date] | Open

## RFI Log
RFI Log
Days open auto-calculates from raised/answered dates (use real dates).
RFI no. | Date raised | To | Subject | System | Tower/Zone | Priority | Date required | Date answered | Days open | Status | Response summary
RFI-001 |  | [Main Contractor] | Slab edge level at Zone A | Curtain wall | T1 / Zone A | High |  |  |  | Open
RFI-002 |  | [Consultant] | Bracket fixing to embed | Curtain wall | T3 / Zone B | Medium |  |  |  | Open
Formulas:
Days open = IF([Date raised]="","",IF([Date answered]="",TODAY()-[Date raised],[Date answered]-[Date raised]))

## Submittal Register
Submittal / Document Register
Status codes: A = Approved ¦ B = Approved as noted ¦ C = Revise & resubmit. Only A/B released for fabrication/install.
Doc no. | Title | Type | System | Rev | Date submitted | Date required | Date returned | Status (A/B/C) | Resubmit? | Days to return | Remarks
SD-CW-001 | Curtain wall typical details | Shop drawing | Curtain wall | 0
CALC-CW-001 | Curtain wall structural calcs | Calculation | Curtain wall | 0
SMP-001 | Aluminium finish sample | Sample | Cladding | 0
Formulas:
Days to return = IF([Date submitted]="","",IF([Date returned]="",TODAY()-[Date submitted],[Date returned]-[Date submitted]))

## NCR Log
Non-Conformance Report (NCR) Log
Disposition: Rework ¦ Repair ¦ Use-as-is (concession) ¦ Reject. Close out every critical NCR before handover.
NCR no. | Date | Tower/Zone | System | Non-conformance description | Raised by | Severity | Root cause | Disposition | Corrective action | Owner | Date closed | Status
NCR-001 |  | T1 / Zone A | Curtain wall | Example: mullion out of plumb > tolerance | QA/QC | Major |  | Rework |  | Site Mgr |  | Open

## Variation Register
Variation / Change Register
Log every potential change. No execution without formal written instruction.
VO no. | Date | Description | Origin | Type | Status | Time impact (days) | Cost impact | Instruction ref | Remarks
VO-001 |  | Example: add louvers to level 30 | Client request | Addition | Notified
VO-002 |  | Example: omit balustrade Zone C | Design change | Omission | Submitted
|  | TOTAL cost impact |  |  |  |  | 0

## Payment Application
Interim Payment Application (IPA)
[AED] values. Replace contract values; enter cumulative % complete and previous cumulative.
Application no. | [##]
Period | [Month-Year]
Date | [date]
From | [Façade Contractor]
To | [Main Contractor]
Ref | Description | Contract value | Cum % complete | Cum value | Previous cum value | This application
1 | Stick curtain wall
2 | Lift-and-slide doors
3 | Glass balustrade
4 | Aluminium cladding panels
5 | Roof crown louvers
6 | Engineering / mock-up / prelims
| Subtotal — work done | 0 |  | 0 | 0 | 0
[5 empty] | Retention % | 5%
| Gross value of works to date |  |  |  |  | 0
| Less retention |  |  |  |  | 0
| Value after retention |  |  |  |  | 0
[5 empty] | Add: variations approved | 0
[5 empty] | Less: previous payments certified | 0
| AMOUNT DUE THIS APPLICATION |  |  |  |  | 0

## Daily Site Report
Daily Site Report
One per day per tower. Keep with photos as a contemporaneous record.
Date | [date]
Day | [ ]
Weather | [ ]
Tower / Zone | [ ]
Prepared by | [ ]
MANPOWER
Trade | Planned | Actual
Curtain wall
Doors
Balustrade
Cladding
Louvers
Supervision/QA/HSE
TOTAL | 0 | 0
ACTIVITIES TODAY
WBS / Zone | Activity / location | Qty done | Unit | Crew | Remarks
MATERIALS / DELIVERIES RECEIVED
Time | Material | Supplier / DN no. | Qty | Inspected (Y/N) | Remarks
PLANT / EQUIPMENT ON SITE
Equipment | No. | Hours | Status | Remarks
DELAYS / ISSUES / INSTRUCTIONS
Ref | Description | Impact | Action / by whom
HSE — TOOLBOX / OBSERVATIONS / INCIDENTS
Time | Observation / incident | Action taken | Reported to
Site Manager signature:
Main Contractor acknowledgement:

## 2-Week Look-Ahead
Two-Week Look-Ahead
Rolling short-term plan. Update weekly. Flag constraints that must clear before start.
WBS | Activity | System | Tower/Zone/Floor | Crew / resource | Planned start | Planned finish | Predecessor / constraint | Constraint clear? (Y/N) | Status | Notes
6.1 | Survey & set out brackets | Curtain wall | T1 / Zone A / L1-5 | 2 + survey |  |  | Slab handover, access |  | Planned
7.1 | Install mullions | Curtain wall | T3 / Zone B / L1-3 | 6 |  |  | Brackets fixed, material on site |  | Planned

## ITP
Inspection & Test Plan (ITP)
H = Hold point ¦ W = Witness point ¦ R = Review/record. Hold points must be released before proceeding.
Ref | Activity / stage | Spec / drawing ref | Inspection / test | Acceptance criteria | Frequency | Responsible | H/W/R | Record / form | Status
ITP-01 | Setting-out survey | [spec] | Dimensional check vs grid | Within survey tolerance | Per zone | QA/QC | H | Survey record
ITP-02 | Bracket / anchor fixing | [spec] | Position, torque, pull-out | Per approved detail & torque | Each bracket / sample | QA/QC | H | Inspection request
ITP-03 | Mullion & transom install | [spec] | Plumb, level, line, joint | Within stated tolerances | Per floor | QA/QC | W | Checklist
ITP-04 | Glass / panel install | [spec] | Setting blocks, edge cover, fit | Per approved detail | Each panel sample | QA/QC | W | Checklist
ITP-05 | Sealant application | [spec] | Joint prep, size, adhesion | Adhesion/cure pass | Sample per batch | QA/QC | R | Sealant log
ITP-06 | Field water test | [AAMA/ASTM/CWCT] | Hose / spray test | No water penetration | Per agreed frequency | QA/QC + MC | H | Test report
ITP-07 | Door operation test | [spec] | Operation, seal, lock | Smooth, sealed, secure | Each unit sample | QA/QC | W | Checklist

## Snagging List
Snagging / Punch List
Track defects to close-out by zone before handover.
Item | Date | Tower/Zone/Floor | System | Location detail | Defect description | Raised by | Priority | Target date | Date closed | Status
S-001 |  | T1 / Zone A / L05 | Curtain wall | Grid 5, vision panel | Example: scratched glass | QA/QC | Medium |  |  | Open