## Recovery Plan
SCHEDULE RECOVERY PLAN
Project: |  | Doc no: PM-PLN-010 | Rev: 01 | Date: | Prepared by:
Yellow cells = fill in. Grey italic row = example — overwrite it. Formulas calculate automatically.
ID | Delayed activity | Baseline finish | Forecast finish | Delay (days) | Cause | Recovery measure | Responsible | Cost of measure (SAR) | Recovered finish | Days recovered | Status | Remarks
REC-001 | L12–L16 curtain wall install | 2026-08-20 | 2026-09-10 | 21 | Late glass delivery | Add 2nd installation crew + night shift for hoisting | Const. Mgr | 85000 | 2026-08-27 | 14 | In progress
| TOTAL | [6 empty] | 85000 |  | 14