## Scope summary
Scope study — [Project name]
Ref | Package / section | Scope description | In scope (Y/N) | BOQ ref | Qty / extent | By others / interface | Notes
S-01 | [Cladding] | [Supply & install of ...] | Y | [2.01] | [500 m²]
S-02 | [Glazing] | [Curtain wall system ...] | Y | [2.02] | [1,200 m²]
S-03 | [Steel support] | [Secondary steel for ...] | N |  |  | [By main contractor] | [Confirm in writing]

## Highlights
Scope highlights & watchpoints — [Project name]
Ref | Category | Highlight / watchpoint | Contract ref | Impact if unmanaged | Action / owner | Status
H-01 | Exclusion | [What is explicitly excluded — restate to client] | [§] | [Scope creep] | [Confirm at kickoff — PM] | Open
H-02 | Interface | [Hand-off with other trade] | [§] | [Delay / gap] | [Interface matrix — PM] | Open
H-03 | Assumption | [Assumption the price relies on] | [§] | [Cost exposure] | [Validate — QS] | Open
H-04 | Qualification | [Qualification from tender] | [§] | [Dispute risk] | [Keep in record — QS] | Open
H-05 | Risk | [Onerous clause / unusual requirement] | [§] | [Commercial risk] | [Mitigation — PM] | Open