## WBS
Work breakdown structure — [Project name]
WBS ID | Level | Work package / task | Deliverable | Owner | Est. hours | Start | Finish | Status
1 | 1 | Project management | Governance & controls | [PM] | 200 |  |  | In progress
1.1 | 2 | Planning & scheduling | Baseline programme | [Planner] | 80 |  |  | Not started
1.2 | 2 | Reporting & controls | Monthly reports | [PM] | 60 |  |  | Not started
2 | 1 | Design & engineering | IFC / approved drawings | [Design lead] | 500 |  |  | Not started
2.1 | 2 | Shop drawings | Approved shop drawings | [Draughtsman] | 300 |  |  | Not started
2.2 | 2 | Material submittals | Approved submittals | [QA/QC] | 120 |  |  | Not started
3 | 1 | Procurement | Purchase orders placed | [Procurement] | 150 |  |  | Not started
4 | 1 | Fabrication | Fabricated units | [Factory] | 600 |  |  | Not started
5 | 1 | Installation | Installed works | [Site manager] | 900 |  |  | Not started
6 | 1 | Testing & commissioning | Signed-off systems | [QA/QC] | 120 |  |  | Not started
7 | 1 | Handover & close-out | Snag-free handover | [PM] | 80 |  |  | Not started